# YKP Hermez Migration Blueprint

Project: YKP Hermez AI Command Center   Scope: Migration of HR and Finance operations into YKP-owned systems, plus read-only Hermez AI summary layer.   Date: 2026-06-30   Version: 1.0   Audience: Developers, DevOps, QA, Operations, Finance, HR

# Table of Contents

[Context & Current Status](#1-context--current-status)

[Project Goals](#2-project-goals)

[Principles for Developers](#3-principles-for-developers)

[Target Architecture](#4-target-architecture)

[Migration Process](#5-migration-process)

[HR App Migration (detailed)](#6-hr-app-migration-detailed)

[Finance App Migration (detailed)](#7-finance-app-migration-detailed)

[Minimal Sheet Structure](#8-minimal-sheet-structure)

[Summary Sheet Contracts for Hermez](#9-summary-sheet-contracts-for-hermez)

[Hermez AI Command Center Logic](#10-hermez-ai-command-center-logic)

[Implementation Roadmap](#11-implementation-roadmap)

[Pilot Plan](#12-pilot-plan)

[Definition of Done](#13-definition-of-done)

[Risks & Mitigations](#14-risks--mitigations)

[Short Developer Message / Next Actions](#15-short-developer-message--next-actions)

[Appendix A: Google Sheets Formula Examples](#appendix-a-google-sheets-formula-examples)

[Appendix B: Environment Variables & Secrets](#appendix-b-environment-variables--secrets)

# 1. Context & Current Status

The YKP Hermez AI Command Center project migrates YKP's HR and Finance operations onto existing sibling web apps and stands up a read-only AI summary layer (Hermez) that produces daily owner briefs, alerts, and weekly insights. The core strategy is reuse over rebuild: clone the existing apps into a YKP testing environment, repoint them at fresh YKP-owned databases, fill master data, validate against source-of-truth (Moka, manual ledgers, physical petty cash), then let Hermez consume daily summary sheets — never raw inputs.

| Component | Current State | Next Action |
| --- | --- | --- |
| HR Web App | Exists, running | Clone/configure for YKP; migrate employee masters, shift rules, payroll; test |
| Finance Web App | Exists, not running | Replace DB source; fill YKP data; map brand/outlet/supplier; validate numbers; pilot |
| Operational Web App | Not built / not final | Build after HR + Finance stable. V1: checklist, closing, waste, incident, QC |
| Marketing Web App | Not built | After core finance + operations run. V1: campaign, content calendar, review log |
| Hermez AI Layer | Not running | Activates once hr_daily_summary + fin_daily_summary exist. Not an input surface |

Status verdict: HR is the greenest path (app already running); Finance is the highest-risk migration (app exists but unverified, numbers must reconcile to Moka). Hermez is gated behind both summary sheets being live and validated.

# 2. Project Goals

Reuse the existing HR and Finance web apps so YKP does not start from zero.

Replace the legacy dummy/spreadsheet sources with YKP-owned databases — no dummy data in production.

Populate YKP master data: brand, outlet, employee, supplier, menu, expense categories, petty cash accounts, payroll rules.

Pilot one brand/outlet for at least 7 days before any multi-outlet rollout.

Prepare a summary layer (hr_daily_summary, fin_daily_summary) so Hermez can generate daily brief, alerts, insights, and weekly reports.

# 3. Principles for Developers

Never edit the running production app directly. Clone to a YKP testing environment first; promote only after validation.

Never swap a spreadsheet ID without auditing the schema. Confirm tab names, column names, formulas, and permissions match the app's expectations.

Hermez is not an input surface. All operational input stays in HR / Finance / Operational / Marketing apps. Hermez reads summaries only.

Hermez reads summaries, not raw data. Raw input sheets are off-limits to the AI layer by default.

Every finance number must be auditable: source, timestamp, user/PIC, and receipt/nota where applicable.

Start with one pilot brand/outlet, then roll out to all brands.

Stable IDs over display names. Brand/outlet/employee identity flows via IDs; names are display-only.

One timezone: Asia/Jakarta (WIB) for all stored dates and times.

Currency integer IDR: no decimals, no Rp prefix, no thousand separators in stored values.

No dummy data in production. Every row must map to a real YKP entity or be explicitly quarantined.

# 4. Target Architecture

## 4.1 Topology (text diagram)

HR Web App (running)        Finance Web App (exists, not running)
        |                              |
        v                              v
 YKP_HR_DATABASE              YKP_FINANCE_DATABASE
 (sheets: master_employee,    (sheets: master_brand, master_outlet,
  master_outlet, hr_rules,     master_supplier, fin_categories,
  hr_attendance, hr_payroll)   fin_pos_daily, fin_supplier_cost,
        |                       fin_petty_cash, fin_expense)
        v                              v
 hr_daily_summary             fin_daily_summary
        \                              /
         \                            /
          v                          v
            HERMEZ AI COMMAND CENTER
                      |
                      v
         Telegram Owner Brief / Alert / Weekly Insight
                      |
                      v
         hermez_daily_brief  +  hermez_alert_log

Operational and Marketing apps, when built, follow the same shape: **input app → YKP database → *_daily_summary → Hermez**. The pattern is the invariant; only the domain changes.

## 4.2 Mermaid diagram

flowchart TD
  subgraph Input["Input Layer (users type here)"]
    HR[HR Web App]
    FIN[Finance Web App]
    OP[Operational App - future]
    MKT[Marketing App - future]
  end

  subgraph Master["YKP_MASTER_DATABASE"]
    MB[master_brand]
    MO[master_outlet]
    ME[master_employee]
    MS[master_supplier]
  end

  subgraph Domain["Domain Databases"]
    HRDB[YKP_HR_DATABASE]
    FINDB[YKP_FINANCE_DATABASE]
  end

  subgraph Summary["Summary Layer (Hermez reads only these)"]
    HRS[hr_daily_summary]
    FINS[fin_daily_summary]
  end

  HERMEZ[Hermez AI Command Center]
  TG[Telegram: Owner Brief / Alert / Weekly Insight]
  HDB[hermez_daily_brief]
  HAL[hermez_alert_log]

  HR --> HRDB
  FIN --> FINDB
  OP --> Domain
  MKT --> Domain

  MB -.shared.-> HRDB
  MB -.shared.-> FINDB
  MO -.shared.-> HRDB
  MO -.shared.-> FINDB
  ME --> HRDB
  MS --> FINDB

  HRDB --> HRS
  FINDB --> FINS

  HRS --> HERMEZ
  FINS --> HERMEZ
  HERMEZ --> TG
  HERMEZ --> HDB
  HERMEZ --> HAL

  style Summary fill:#e0f2fe,stroke:#0369a1
  style Master fill:#fef3c7,stroke:#b45309
  style HERMEZ fill:#ede9fe,stroke:#6d28d9

## 4.3 Data topology decision

### 4.3.1 Options considered

| Option | Pros | Cons | Verdict |
| --- | --- | --- | --- |
| A. Single YKP_CENTRAL_DATABASE workbook | One ID, simplest wiring, easy dev convenience | One giant sheet, permission granularity impossible, HR and Finance apps both write same workbook → accidental cross-contamination risk, quota limits | Rejected for prod; acceptable only as dev convenience |
| B. Three databases: YKP_MASTER_DATABASE + YKP_HR_DATABASE + YKP_FINANCE_DATABASE | Clean separation of concerns, per-domain permissions, independent app ownership, master shared cleanly, blast radius contained | Three IDs to configure; master must be referenced (read) by both domain apps | Chosen |

### 4.3.2 Why split into three

Permission isolation — HR staff should not have write access to finance sheets; finance staff should not touch HR. A single workbook makes row/cell-level permissions brittle. Splitting lets each domain app hold its own service credentials and grant least-privilege per sheet.

Blast radius — a formula error or bad import in Finance cannot corrupt HR masters or attendance logs. Each domain's failure is contained to its own database.

Ownership boundary — HR app owns YKP_HR_DATABASE; Finance app owns YKP_FINANCE_DATABASE; neither owns YKP_MASTER_DATABASE (shared read + controlled-write via a master-management surface). This maps cleanly to app service accounts.

Independent rollout cadence — HR can stabilize (it already runs) while Finance is still being validated, without touching shared state. The pilot gates operate per-domain.

Single source of truth for masters — YKP_MASTER_DATABASE holds master_brand, master_outlet, master_employee, master_supplier exactly once. Both domain databases reference master IDs (read) rather than duplicating them, which prevents the "name inconsistency" risk. A single master_brand / master_outlet is the authoritative reference.

Quota and performance — Google Sheets / spreadsheet-backed apps hit practical limits on a single workbook; splitting keeps each workbook small and fast.

### 4.3.3 Reference model

master_brand and master_outlet live only in YKP_MASTER_DATABASE.

master_employee lives in YKP_MASTER_DATABASE as the canonical employee record; HR-specific extension columns (shift assignment, payroll config) live in YKP_HR_DATABASE keyed by employee_id.

master_supplier lives in YKP_MASTER_DATABASE.

Domain databases read master IDs; they never rewrite master rows. Writes to masters go through the master-management surface only.

| Database | Sheet | Owner app | Hermez reads? |
| --- | --- | --- | --- |
| YKPMASTERDATABASE | master_brand | Master mgmt surface | Yes |
| YKPMASTERDATABASE | master_outlet | Master mgmt surface | Yes |
| YKPMASTERDATABASE | master_employee | Master mgmt surface / HR app | Yes |
| YKPMASTERDATABASE | master_supplier | Master mgmt surface / Finance app | Yes |
| YKPHRDATABASE | hr_rules | HR app | No (summary only) |
| YKPHRDATABASE | hr_attendance | HR app | No (summary only) |
| YKPHRDATABASE | hr_payroll | HR app | No (summary only) |
| YKPHRDATABASE | hrdailysummary | HR app writes | Yes |
| YKPFINANCEDATABASE | fin_categories | Finance app | No |
| YKPFINANCEDATABASE | finposdaily | Finance app | No (summary only) |
| YKPFINANCEDATABASE | finsuppliercost | Finance app | No (summary only) |
| YKPFINANCEDATABASE | finpettycash | Finance app | No (summary only) |
| YKPFINANCEDATABASE | fin_expense | Finance app | No (summary only) |
| YKPFINANCEDATABASE | findailysummary | Finance app writes | Yes |
| (Hermez output store) | hermezdailybrief | Hermez | Yes (own log) |
| (Hermez output store) | hermezalertlog | Hermez | Yes (own log) |

## 4.4 Read rules

Read rules are enforced by sheet permissions, not just convention:

| Layer | Hermez access | App write access |
| --- | --- | --- |
| YKP_MASTER_DATABASE | read-only (masters) | HR app / Finance app (shared) |
| YKP_HR_DATABASE raw sheets (attendance, payroll) | denied | HR app only |
| YKP_FINANCE_DATABASE raw sheets (POS, supplier, petty cash, expense) | denied | Finance app only |
| hr_daily_summary / fin_daily_summary | read-only — only sheets Hermez reads | HR / Finance app writes; Hermez never writes |
| hermez_daily_brief / hermez_alert_log | Hermez writes | Hermez only |

## 4.5 Naming conventions

### 4.5.1 Stable IDs

Format: UPPERCASE_PREFIX-NNN for human-readable business IDs, or a UUID for internal surrogate keys. Pick one per entity and never change it.

Never reuse a display name as a key. Names change; IDs must not.

Once assigned, an ID is immutable for the entity's lifetime. Inactive entities are marked status = inactive, never deleted or re-ID'd.

| Entity | ID column | Format example | Lifetime |
| --- | --- | --- | --- |
| Brand | brand_id | BR-001 | immutable |
| Outlet | outlet_id | OL-001 | immutable |
| Employee | employee_id | EMP-00001 (or UUID) | immutable; survives rehire |
| Supplier | supplier_id | SUP-0001 | immutable |
| Rule | rule_id | HRR-OUT-001 (per outlet) | immutable while active |
| Alert | alert_id | ALT-YYYYMMDD-NNN | immutable |

FK rules: employee.outlet_id must resolve to a row in master_outlet; outlet.brand_id must resolve to master_brand; fin_*.outlet_id must resolve to master_outlet. Mismatches block the write.

### 4.5.2 Date / Time

| Field | Format | Timezone | Notes |
| --- | --- | --- | --- |
| Date columns | YYYY-MM-DD | Asia/Jakarta (WIB) | ISO 8601, no slashes |
| Timestamp columns | YYYY-MM-DD HH:mm:ss | Asia/Jakarta, stored naive-WIB | Append Z only if actually UTC |
| Time-of-day columns | HH:mm | 24-hour, Asia/Jakarta | For shift start/end |
| Payroll period | YYYY-MM (period) or YYYY-MM-DD to YYYY-MM-DD range | WIB | Explicit start/end, no "last month" phrasing in data |
| generated_at (Hermez) | YYYY-MM-DD HH:mm:ss | WIB | When brief/alert was produced |

Rule: one timezone for all YKP data — Asia/Jakarta. If an outlet operates in a different zone (rare for YKP), store the value in WIB and record the source zone in master_outlet.timezone; never store local-naive times mixed with WIB-naive times in the same column.

### 4.5.3 Currency

| Rule | Value |
| --- | --- |
| Currency | IDR (Rupiah) only for YKP V1 |
| Storage format | integer rupiah, no decimals, no Rp prefix, no thousand separators in stored values |
| Display format | Rp 1.234.567 (Indonesian grouping) in UI; raw integer in data |
| Rounding | round to whole rupiah; no sen (IDR has no subunit) |
| Negative values | allowed only for corrections/refunds; never for revenue totals |
| Column suffix | amount/cost/balance/sales columns end in the unit, e.g. gross_sales, petty_cash_out — all IDR integers |

Never store "Rp 1.000.000" as a string in a data cell; the app and Hermez must parse integers. Display formatting belongs in the UI layer only.

## 4.6 Audit & permission rules

### 4.6.1 Audit trail — every finance number

Every finance figure must trace to source, timestamp, PIC, and nota where applicable. This is enforced structurally, not by convention.

| Required audit field | Where stored | Example |
| --- | --- | --- |
| source | row column source | moka / manual / receipt |
| source_ref | source_ref | Moka trx ID, receipt number, nota no. |
| recorded_at | recorded_at | 2026-06-30 21:05:00 (WIB) |
| recorded_by | recorded_by | PIC username / telegram_id |
| updated_at | updated_at | last edit timestamp |
| receipt_url | receipt_url | link to nota image (optional) |

Any finance row missing source, recorded_at, or recorded_by is rejected at write time by the Finance app. The daily summary must be reconstructable from raw rows via these fields.

### 4.6.2 Hermez no-write-back policy

Hermez reads hr_daily_summary and fin_daily_summary only.

Hermez writes only to hermez_daily_brief and hermez_alert_log.

Hermez never edits operational data, triggers transfers, or auto-approves anything. Every action item in a brief requires owner/manager approval. This is a hard boundary: even if a future feature requests auto-action, V1 refuses.

### 4.6.3 Permission matrix

| Role | Master DB | HR DB raw | HR summary | Finance DB raw | Finance summary | Hermez output | Telegram send |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Owner | read | read | read | read | read | read | receive |
| Manager (outlet) | read | read (own outlet) | read (own outlet) | read (own outlet) | read (own outlet) | — | — |
| HR staff | read | write | read | — | — | — | — |
| Finance staff | read | — | read | write | read | — | — |
| Hermez service account | read (masters) | denied | read-only | denied | read-only | write (own) | send |
| Developer (testing env only) | full | full | full | full | full | full | test channel |

Sheet-level permissions enforce the matrix; do not rely on app-code goodwill.

The Hermez service account has no write to any HR or Finance sheet and no read on raw input sheets — only the two summary sheets and the master read set.

Production credentials are scoped per environment; the testing environment uses separate IDs from production.

### 4.6.4 Validation gates (audit-friendly)

Pre-migration backup of any existing database/spreadsheet before schema changes and before rollout.

Nightly reconciliation during pilot: app totals vs Moka vs physical petty cash vs manual calc. Any variance above tolerance blocks rollout.

Immutable IDs: re-assigning or reusing an ID is a blocking defect, not a cleanup task.

Dummy-data quarantine: dummy rows must be detached/removed before production; a single row of dummy data in production fails DoD.

## 4.7 Cross-cutting invariants

| Invariant | Enforcement |
| --- | --- |
| Single source of truth for brand/outlet identity | YKP_MASTER_DATABASE only; FK checks in domain apps |
| Hermez reads summaries, not raw | Service-account sheet permissions deny raw sheets |
| No dummy in production | DoD gate + nightly reconciliation |
| Every finance number auditable | Required audit columns on every finance row |
| Pilot before rollout | 1 brand/outlet, ≥7 days, variance within tolerance |
| One timezone | Asia/Jakarta across all YKP data |
| Currency integer IDR | No string-formatted currency in data cells |

# 5. Migration Process

The migration follows a repeatable, per-domain pattern:

| Phase | HR | Finance | Gate |
| --- | --- | --- | --- |
| 1. Clone | Copy HR app to YKP testing environment | Copy Finance app to YKP testing environment | App loads; no production impact |
| 2. Repoint | Connect to YKP_HR_DATABASE | Connect to YKP_FINANCE_DATABASE | Read/write verified |
| 3. Clean | Remove all dummy/demo data | Remove all dummy/demo data | No orphan rows |
| 4. Fill masters | master_brand, master_outlet, master_employee | master_brand, master_outlet, master_supplier, categories, payment methods, petty cash accounts | FK integrity passes |
| 5. Configure rules | hr_rules per outlet | Opening balances, expense categories, payment methods | Rules visible in app |
| 6. Seed transactions | Sample attendance + payroll | Sample POS, supplier, petty cash, expense rows | Matches source documents |
| 7. Validate | Attendance/payroll reconcile to manual list | Dashboard numbers reconcile to Moka/manual P&L | Within tolerance |
| 8. Pilot | 1 outlet, 7 days real staff | 1 brand/outlet, 7 days live transactions | Daily validation passes |
| 9. Summary | Build hr_daily_summary | Build fin_daily_summary | Hermez can read |
| 10. Rollout | Outlet-by-outlet | Brand-by-brand | Each passes 1-day smoke test |

Cross-domain dependency: Hermez can be wired after step 9 for both domains. Do not activate Hermez before both summary sheets exist and are validated.

# 6. HR App Migration (detailed)

## 6.1 master_employee schema

| Column | Type | Required | Notes |
| --- | --- | --- | --- |
| employee_id | text / UUID | Y | Unique ID, stable across systems |
| full_name | text | Y | Display name |
| role | text | Y | e.g. barista, cook, supervisor, manager |
| outlet_id | text | Y | FK to master_outlet |
| brand_id | text | Y | Denormalized for summary filters |
| phone | text | N | WhatsApp / SMS contact |
| telegram_id | text | N | For Hermez alert routing |
| employment_type | text | Y | fulltime / parttime / contract |
| join_date | date | Y | Payroll prorate baseline |
| base_salary | number | Y | Monthly gross (Rp) |
| status | text | Y | active / inactive / terminated |

## 6.2 master_outlet mapping

| Column | Type | Required | Notes |
| --- | --- | --- | --- |
| outlet_id | text | Y | Unique ID |
| brand_id | text | Y | FK to master_brand |
| outlet_name | text | Y | Display name |
| location | text | N | City / address |
| timezone | text | Y | Default Asia/Jakarta |
| opening_time | time | N | Earliest shift start |
| closing_time | time | N | Latest shift end |
| status | text | Y | active / closed / test |

Mapping rule: every employee.outlet_id must exist in master_outlet.outlet_id. One employee maps to exactly one outlet at a time; multi-outlet staff need a primary outlet + secondary assignment log.

## 6.3 hr_rules schema

| Column | Type | Required | Notes |
| --- | --- | --- | --- |
| rule_id | text | Y | Unique ID |
| outlet_id | text | Y | Rule scope |
| shift_name | text | Y | morning / afternoon / full_day |
| shift_start | time | Y | Expected check-in |
| shift_end | time | Y | Expected check-out |
| latetoleranceminutes | int | Y | e.g. 10 |
| overtimeratemultiplier | number | Y | e.g. 1.5 for first 4h, 2.0 after |
| overtimedailycap_hours | number | N | e.g. 4 |
| earlyclockintolerance_min | int | N | Prevent gaming the clock |
| mandatory_checkout | boolean | Y | true requires end-of-day check-out |
| payrollperiodstart | int | Y | 1–31 day of month |
| payrollperiodend | int | Y | e.g. 31 |

## 6.4 hr_attendance schema

| Column | Type | Required | Notes |
| --- | --- | --- | --- |
| attendance_id | text | Y | Unique ID |
| date | date | Y | Work date (Asia/Jakarta) |
| employee_id | text | Y | FK to master_employee |
| outlet_id | text | Y | Outlet worked |
| shift_name | text | Y | FK to hrrules.shiftname |
| check_in | datetime | Y | Actual check-in |
| check_out | datetime | N | Missing = open attendance |
| checkinlocation | text | N | Optional geotag |
| checkoutlocation | text | N | Optional geotag |
| is_late | boolean | Y | Computed from rule |
| late_minutes | int | N | 0 if on time |
| isearlyleave | boolean | N | True if checkout < shiftend |
| overtime_hours | number | N | Computed from rule |
| attendance_status | text | Y | present / absent / izin / sakit / cuti |
| approved_by | text | N | Manager/supervisor ID |
| notes | text | N | Free text |

## 6.5 Payroll calculation formulas

Base period definition

payroll_days = DATEDIFF(payroll_period_start, payroll_period_end) + 1

Daily prorated salary

daily_rate = base_salary / payroll_days

Attendance proration

attendance_count = COUNT(hr_attendance WHERE employee_id = X
                                          AND date IN period
                                          AND status IN ('present','izin','sakit'))
absent_days      = payroll_days - attendance_count
attendance_deduction = absent_days * daily_rate

Late deduction (configurable per outlet)

late_deduction = IF(late_minutes_total_in_period > 60,
                    FLOOR(late_minutes_total / 60) * hourly_late_penalty,
                    0)

Overtime pay

regular_hourly_rate  = base_salary / (payroll_days * shift_hours)
overtime_first_block = MIN(overtime_hours, 4) * regular_hourly_rate * 1.5
overtime_next_block  = MAX(overtime_hours - 4, 0) * regular_hourly_rate * 2.0
overtime_pay         = overtime_first_block + overtime_next_block

Gross salary

gross_salary = (attendance_count * daily_rate)
               + overtime_pay
               + bonus
               - attendance_deduction
               - late_deduction
               - other_deductions

Net salary estimate

net_salary = gross_salary - (gross_salary * tax_estimate_pct) - employee_benefits

### 6.5.1 Example: Barista “Ayu” at outlet OL-001

| Item | Value |
| --- | --- |
| Base salary | Rp 4,500,000 |
| Payroll period | 1–30 Jun 2026 (30 days) |
| Daily rate | Rp 150,000 |
| Present days | 26 |
| Izin (paid) | 2 |
| Absent | 2 |
| Total late minutes | 75 |
| Hourly late penalty | Rp 18,750 |
| Overtime hours | 5 |
| Regular shift hours | 8 |
| Hourly rate | Rp 18,750 |
| Bonus | Rp 250,000 |

| Calculation | Amount |
| --- | --- |
| Attendance base | 28 × Rp 150,000 = Rp 4,200,000 |
| Absent deduction | 2 × Rp 150,000 = -Rp 300,000 |
| Late deduction | 75 min = 1.25h → 1h × Rp 18,750 = -Rp 18,750 |
| Overtime pay | (4 × Rp 18,750 × 1.5) + (1 × Rp 18,750 × 2.0) = Rp 150,000 |
| Bonus | +Rp 250,000 |
| Gross salary | Rp 4,281,250 |

## 6.6 Step-by-step migration task list

| Step | Task | Owner | Verification |
| --- | --- | --- | --- |
| 1 | Clone HR app to YKP testing environment | Dev | App loads with no live data |
| 2 | Connect app to YKPHRDATABASE or YKPCENTRALDATABASE HR tab | Dev | App reads/writes new spreadsheet |
| 3 | Fill masterbrand and masteroutlet for all YKP brands/outlets | Data | No orphan employees |
| 4 | Fill master_employee with current roster | Data | 1:1 match with existing payroll list |
| 5 | Configure hr_rules per outlet (shift, tolerance, overtime, period) | Ops + Dev | Rules visible in app admin panel |
| 6 | Test attendance: check-in, check-out, late, izin, missing checkout | QA | All statuses computed correctly |
| 7 | Test payroll on 3–5 sample employees | QA + Finance | Compare to manual spreadsheet |
| 8 | Reconcile mismatches and adjust formulas/config | Dev | Variance ≤ Rp 1,000 per employee |
| 9 | Pilot 1 outlet for 7 days with real staff | Ops | Daily attendance closes cleanly |
| 10 | Rollout to remaining outlets | Ops + Dev | Each outlet passes 1-day smoke test |

## 6.7 Validation checklist

| # | Check | Pass criteria |
| --- | --- | --- |
| 1 | Schema validation | masteremployee, masteroutlet, hrrules, hrattendance exist and all required columns populated |
| 2 | Referential integrity | Every employee has valid outletid and brandid |
| 3 | Shift rule coverage | Every active outlet has at least one shift rule |
| 4 | Attendance closure | No open check-out older than 48 hours at end of day |
| 5 | Late detection | Late flagged within tolerance and minutes counted |
| 6 | Overtime math | Overtime hours match clock-out minus shift_end, capped by rule |
| 7 | Payroll reconciliation | App gross == manual gross for 3–5 sample employees |
| 8 | Summary output | hrdailysummary populated with correct staff counts |
| 9 | Pilot sign-off | Outlet manager confirms numbers match reality for 7 days |
| 10 | Backup before rollout | Snapshot of YKPHRDATABASE taken and stored |

## 6.8 Common failure modes

| Failure | Likely cause | Fix |
| --- | --- | --- |
| Clock-in recorded on wrong date | Timezone set to UTC instead of Asia/Jakarta | Force Asia/Jakarta in app and database |
| Missing checkout flagged as present | mandatory_checkout=false or missing rule | Set mandatory_checkout=true per outlet |
| Payroll variance > Rp 10,000 | Wrong payroll_days or prorate formula | Reconcile period length and daily_rate |
| Overtime not calculated | shift_end or overtime_rate_multiplier empty | Audit hr_rules completeness |
| Employee appears at wrong outlet | masteroutlet.outletid mismatch | Use master_outlet as single source of truth |
| Summary shows duplicate staff | employee_id not unique or rehired with same phone | Add unique constraint on employee_id |
| Late tolerance ignored | Rule not linked to outlet/shift combination | Add composite key (outletid, shiftname) |
| Rollout breaks existing pilot | Production database still points to test sheet | Use environment-specific spreadsheet IDs |
| Hermez reads stale data | hrdailysummary not refreshed after attendance close | Schedule daily close + summary refresh job |

# 7. Finance App Migration (detailed)

## 7.1 Objective

Migrate the existing Finance Web App from its dummy/demo environment into a YKP-dedicated environment, connect it to the YKP Finance database, and validate dashboard numbers against Moka/manual sources before piloting at one brand/outlet.

## 7.2 Master data schemas

### 7.2.1 master_brand

| Column | Type | Description |
| --- | --- | --- |
| brand_id | string / UUID | Unique brand identifier. |
| brand_name | string | Display name of the brand. |
| status | enum: active / inactive | Whether the brand is operational. |
| created_at | timestamp | Record creation time. |
| updated_at | timestamp | Last update time. |

### 7.2.2 master_outlet

| Column | Type | Description |
| --- | --- | --- |
| outlet_id | string / UUID | Unique outlet identifier. |
| brand_id | FK → master_brand.brand_id | Parent brand. |
| outlet_name | string | Display name of the outlet. |
| location | string | Address or area label. |
| status | enum: active / inactive | Outlet operational flag. |
| created_at | timestamp | Record creation time. |
| updated_at | timestamp | Last update time. |

### 7.2.3 master_supplier

| Column | Type | Description |
| --- | --- | --- |
| supplier_id | string / UUID | Unique supplier identifier. |
| supplier_name | string | Supplier display name. |
| category | string | Ingredient, packaging, logistics, etc. |
| contact | string | Phone or email. |
| bank_account | string | Optional account details. |
| status | enum: active / inactive | Whether supplier is still used. |
| created_at | timestamp | Record creation time. |
| updated_at | timestamp | Last update time. |

### 7.2.4 Finance categories

#### 7.2.4.1 finexpensecategory

| Column | Type | Description |
| --- | --- | --- |
| category_id | string / UUID | Unique category identifier. |
| category_name | string | Human-readable name (electricity, rent, marketing, etc.). |
| account_type | enum: OPEX / CAPEX / COGS / OTHER | Grouping for P&L. |
| status | enum: active / inactive | Operational flag. |

#### 7.2.4.2 finpaymentmethod

| Column | Type | Description |
| --- | --- | --- |
| method_id | string / UUID | Unique method identifier. |
| method_name | string | Cash, debit card, QRIS, transfer, etc. |
| is_cash | boolean | True if method affects physical cash count. |
| status | enum: active / inactive | Operational flag. |

#### 7.2.4.3 finpettycash_account

| Column | Type | Description |
| --- | --- | --- |
| account_id | string / UUID | Unique petty-cash account identifier. |
| outlet_id | FK → master_outlet.outlet_id | Outlet the cash belongs to. |
| account_name | string | Label (e.g., "Petty Cash — Outlet A"). |
| currency | string | Default IDR. |
| status | enum: active / inactive | Operational flag. |

### 7.2.5 finopeningbalance

| Column | Type | Description |
| --- | --- | --- |
| balance_id | string / UUID | Unique balance record identifier. |
| outlet_id | FK → master_outlet.outlet_id | Outlet scope. |
| effective_date | date | Date the balance applies. |
| cash_balance | decimal | Cash-on-hand starting balance. |
| petty_cash_balance | decimal | Petty cash starting balance. |
| unpaid_supplier_opening | decimal | Supplier debt carried forward. |
| receivable_opening | decimal | Optional customer receivables. |
| notes | text | Supporting notes / evidence references. |
| recorded_by | string | PIC / user who entered it. |
| created_at | timestamp | Record creation time. |

## 7.3 Transaction schemas

### 7.3.1 finposdaily

| Column | Type | Description |
| --- | --- | --- |
| pos_id | string / UUID | Unique daily record identifier. |
| date | date | Transaction date. |
| brand_id | FK → master_brand.brand_id | Brand scope. |
| outlet_id | FK → master_outlet.outlet_id | Outlet scope. |
| gross_sales | decimal | Total gross sales before discounts/refunds. |
| net_sales | decimal | Gross sales minus discounts and refunds. |
| transaction_count | integer | Number of transactions. |
| discount_total | decimal | Total discounts applied. |
| refund_total | decimal | Total refunds. |
| payment_method_breakdown | JSON / sub-table | Optional per-method split. |
| source | enum: Moka / manual / import | Origin of the data. |
| imported_at | timestamp | When the row was imported. |
| verified_by | string | PIC who validated the numbers. |

### 7.3.2 finsuppliercost

| Column | Type | Description |
| --- | --- | --- |
| cost_id | string / UUID | Unique cost record identifier. |
| date | date | Invoice or transaction date. |
| supplier_id | FK → master_supplier.supplier_id | Supplier reference. |
| brand_id | FK → master_brand.brand_id | Brand scope. |
| outlet_id | FK → master_outlet.outlet_id | Outlet scope if applicable. |
| invoice_number | string | Supplier invoice / nota number. |
| amount | decimal | Total supplier cost. |
| paid_amount | decimal | Amount already paid. |
| unpaid_amount | decimal | amount - paid_amount. |
| due_date | date | Payment due date. |
| status | enum: paid / partial / unpaid | Payment state. |
| attachment_url | string | Link to nota/invoice image. |
| recorded_by | string | PIC. |
| created_at | timestamp | Record creation time. |

### 7.3.3 finpettycash

| Column | Type | Description |
| --- | --- | --- |
| pc_id | string / UUID | Unique transaction identifier. |
| date | date | Transaction date. |
| outlet_id | FK → master_outlet.outlet_id | Outlet scope. |
| account_id | FK → fin_petty_cash_account.account_id | Petty-cash account. |
| type | enum: in / out | Direction of cash movement. |
| amount | decimal | Transaction amount (always positive). |
| category_id | FK → fin_expense_category.category_id | Expense category. |
| description | text | What the cash was used for. |
| attachment_url | string | Optional nota/photo evidence. |
| recorded_by | string | PIC. |
| created_at | timestamp | Record creation time. |

### 7.3.4 fin_expense

| Column | Type | Description |
| --- | --- | --- |
| expense_id | string / UUID | Unique expense identifier. |
| date | date | Expense date. |
| brand_id | FK → master_brand.brand_id | Brand scope. |
| outlet_id | FK → master_outlet.outlet_id | Outlet scope. |
| category_id | FK → fin_expense_category.category_id | Expense category. |
| amount | decimal | Expense amount. |
| payment_method_id | FK → fin_payment_method.method_id | How it was paid. |
| description | text | Supporting details. |
| attachment_url | string | Nota/receipt image. |
| recorded_by | string | PIC. |
| created_at | timestamp | Record creation time. |

## 7.4 Dashboard formulas

| Metric | Formula | Source Tables |
| --- | --- | --- |
| Revenue | SUM(net_sales) for selected date/brand/outlet | fin_pos_daily |
| Expense | SUM(amount) where payment_method is recorded in fin_expense | fin_expense |
| Supplier Cost | SUM(amount) for the period in fin_supplier_cost | fin_supplier_cost |
| Petty Cash Out | SUM(amount) from fin_petty_cash where type = 'out' | fin_petty_cash |
| Unpaid Supplier | SUM(unpaid_amount) where status != 'paid' | fin_supplier_cost |
| Cash Difference | (opening_cash + cash_revenue_in - cash_expense_out - petty_cash_out) - physical_cash_count | fin_opening_balance, fin_pos_daily (cash methods), fin_expense, fin_petty_cash, closing count |
| Net Profit Estimate | Revenue - Expense - Supplier Cost - Petty Cash Out | All of the above |

Notes:

Cash-revenue-in should be derived from the payment-method breakdown of fin_pos_daily for methods where is_cash = true.

Cash-expense-out should be derived from fin_expense for payment methods where is_cash = true.

Physical cash count is entered at daily closing and is not stored in the schemas above; the difference formula relies on an additional closing-cash input.

## 7.5 Migration task list

| # | Task | Owner | Output / Gate |
| --- | --- | --- | --- |
| 1 | Clone Finance app to YKP testing environment | DevOps / Developer | Separate app instance with no production impact. |
| 2 | Connect cloned app to YKP_FINANCE_DATABASE or Finance tabs in YKP_CENTRAL_DATABASE | Backend Developer | Verified read/write connection. |
| 3 | Remove or detach all dummy/demo data from the cloned instance | Backend Developer | No dummy brand/outlet/supplier/transaction remains. |
| 4 | Fill master data: brand, outlet, supplier, finance categories, payment methods, petty-cash accounts | Data / Operations | Master sheets fully populated and cross-referenced. |
| 5 | Enter opening balances: cash, petty cash, supplier debt, receivables | Finance / Operations | Signed-off opening balances per outlet. |
| 6 | Import sample POS data from Moka for 3–7 days | Backend / Data | fin_pos_daily rows match Moka report. |
| 7 | Input sample supplier costing, petty cash, and expense transactions with notas | Operations / Finance | All sample rows have evidence links. |
| 8 | Validate dashboard formulas: revenue, expense, supplier cost, petty cash, unpaid supplier, cash difference, net profit | QA / Finance | Variance vs. manual calculation within tolerance. |
| 9 | Pilot finance live for 1 brand / 1 outlet for 7 days | Operations | Daily validation passes; issues logged and fixed. |
| 10 | Prepare fin_daily_summary for Hermez consumption | Backend Developer | Summary sheet contract satisfied. |

## 7.6 Daily validation against Moka / manual records

| Step | Action | Evidence / Tolerance |
| --- | --- | --- |
| 1 | Export Moka daily sales report (gross sales, net sales, transaction count, discounts, refunds). | Source file from Moka dashboard. |
| 2 | Compare each row in fin_pos_daily to the Moka report for the same date + outlet_id. | Allowable variance ≤ 1% or Rp 10,000, whichever is larger. |
| 3 | Reconcile supplier invoices against fin_supplier_cost amount and unpaid_amount. | Match invoice number + photo evidence. |
| 4 | Count physical petty cash and compare with (opening_petty_cash + petty_cash_in - petty_cash_out). | Variance ≤ Rp 5,000 or must be explained. |
| 5 | Count physical cash register and compare with cash formula. | Variance = cash_difference column. |
| 6 | Spot-check fin_expense rows against saved notas/photos. | 100% of sample rows must have attachments. |
| 7 | Run dashboard formulas and compare net profit estimate to a manually reconstructed P&L. | Variance ≤ 2%. |
| 8 | If any step fails, stop rollout, log the mismatch, fix root cause, and re-validate. | Pass gate before continuing. |

## 7.7 Rollout gate

Finance App migration is considered done when:

Cloned app runs against YKP data with no dummy records.

Dashboard numbers match Moka/manual sources within the tolerances above.

7-day pilot at one brand/outlet completes with no unresolved cash differences or supplier mismatches.

fin_daily_summary is produced daily and readable by Hermez.

Backup of pre-migration and pre-rollout database/spreadsheet exists.

# 8. Minimal Sheet Structure

This section lists the smallest set of sheets (tabs) required across the three databases. Additional sheets may exist, but these are mandatory for V1.

## 8.1 YKPMASTERDATABASE

| Sheet | Purpose | Written by | Read by |
| --- | --- | --- | --- |
| master_brand | Canonical brand list | Master mgmt surface | HR, Finance, Hermez |
| master_outlet | Canonical outlet list + brand linkage | Master mgmt surface | HR, Finance, Hermez |
| master_employee | Canonical employee records | Master mgmt surface / HR app | HR, Hermez |
| master_supplier | Canonical supplier records | Master mgmt surface / Finance app | Finance, Hermez |

## 8.2 YKPHRDATABASE

| Sheet | Purpose | Written by | Read by |
| --- | --- | --- | --- |
| master_employee (read view / sync) | HR app copy/reference of master employee | Master sync | HR app |
| hr_rules | Shift rules per outlet | HR app | HR app |
| hr_attendance | Daily attendance records | HR app | HR app |
| hr_payroll | Payroll records per period | HR app | HR app |
| hr_daily_summary | Daily per-outlet HR summary | HR app | Hermez |

## 8.3 YKPFINANCEDATABASE

| Sheet | Purpose | Written by | Read by |
| --- | --- | --- | --- |
| fin_expense_category | Expense categories and P&L grouping | Finance app | Finance app |
| fin_payment_method | Payment methods + cash flag | Finance app | Finance app |
| fin_petty_cash_account | Petty cash accounts per outlet | Finance app | Finance app |
| fin_opening_balance | Daily opening balances | Finance app | Finance app |
| fin_pos_daily | Daily POS sales | Finance app / import | Finance app |
| fin_supplier_cost | Supplier invoices and payment status | Finance app | Finance app |
| fin_petty_cash | Petty cash in/out | Finance app | Finance app |
| fin_expense | General expenses | Finance app | Finance app |
| fin_daily_summary | Daily per-outlet finance summary | Finance app | Hermez |

## 8.4 Hermez output store

| Sheet | Purpose | Written by | Read by |
| --- | --- | --- | --- |
| hermez_daily_brief | Generated daily brief | Hermez | Owner, Manager |
| hermez_alert_log | Generated alerts | Hermez | Owner, Manager |

# 9. Summary Sheet Contracts for Hermez

Hermez reads only these two summary sheets. They are produced by the HR and Finance apps respectively.

## 9.1 hrdailysummary contract

One row = one outlet, one date.

| # | Column | Type | Format | Required | Example | Source/Derivation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | date | date | YYYY-MM-DD | Yes | 2026-06-29 | Operational date of the outlet |
| 2 | brand | string | ref master_brand.brand_name | Yes | YKP Kitchen | Join to master_brand |
| 3 | outlet | string | ref master_outlet.outlet_name | Yes | YKP Surabaya 01 | Join to master_outlet |
| 4 | total_staff | int | >= 0 | Yes | 8 | Count active employees at the outlet |
| 5 | staff_present | int | 0..total_staff | Yes | 7 | Count check-ins for the date |
| 6 | staff_late | int | 0..total_staff | Yes | 3 | Count late check-ins beyond tolerance |
| 7 | staff_absent | int | 0..total_staff | Yes | 1 | total_staff − present (excluding izin/sakit/cuti) |
| 8 | payroll_issue | string | free text / "none" | Yes | bonus blm diapprove | Flag from payroll module |
| 9 | major_hr_issue | string | free text / "none" | Yes | SPV no-show | Significant issue, not routine |
| 10 | recommended_action | string | free text | Yes | briefing SPV | Recommendation from HR app |

Rules:

staff_present + staff_absent == total_staff (invariant HR app must enforce).

brand/outlet must match master_brand/master_outlet; if not, Hermez rejects the row, logs to hermez_alert_log with severity warning and alerttype `schemamismatch`.

Null numeric = error, not 0. Hermez skips the row and raises an alert.

## 9.2 findailysummary contract

One row = one outlet, one date.

| # | Column | Type | Format | Required | Example | Source/Derivation |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | date | date | YYYY-MM-DD | Yes | 2026-06-29 | Operational date |
| 2 | brand | string | ref master_brand | Yes | YKP Kitchen | Join master_brand |
| 3 | outlet | string | ref master_outlet | Yes | YKP Surabaya 01 | Join master_outlet |
| 4 | revenue | int (IDR) | >= 0, whole rupiah | Yes | 5400000 | Sum fin_pos_daily.net_sales |
| 5 | expense | int (IDR) | >= 0 | Yes | 1200000 | Sum fin_expense for the date |
| 6 | supplier_cost | int (IDR) | >= 0 | Yes | 800000 | Sum fin_supplier_cost due/recorded that date |
| 7 | petty_cash_out | int (IDR) | >= 0 | Yes | 150000 | Sum outflows from fin_petty_cash |
| 8 | unpaid_supplier | int (IDR) | >= 0 | Yes | 2300000 | Outstanding fin_supplier_cost not paid |
| 9 | cash_difference | int (IDR) | signed | Yes | -25000 | Physical cash − system cash (may be negative) |
| 10 | net_profit_estimate | int (IDR) | signed | Yes | 3250000 | revenue − expense − supplier_cost |
| 11 | major_finance_issue | string | free text / "none" | Yes | selisih kas | Significant issue |
| 12 | recommended_action | string | free text | Yes | audit closing | Recommendation from Finance app |

Rules:

All rupiah values are stored as whole integers, no decimals, no thousand separators.

cash_difference must be signed (may be negative).

net_profit_estimate = revenue − expense − supplier_cost (HR costs are not included in this formula).

Null numeric = error → skip row + alert.

# 10. Hermez AI Command Center Logic

## 10.1 System position

HR Web App                Finance Web App
   |                          |
   v                          v
YKP_HR_DATABASE         YKP_FINANCE_DATABASE
   |                          |
   v                          v
hr_daily_summary        fin_daily_summary        <-- only sheets Hermez reads
   \                          /
    \                        /
     v                      v
     HERMEZ AI COMMAND CENTER
              |
              v
   Telegram Owner Brief / Alert / Weekly Insight
              |
              v
   hermez_daily_brief  +  hermez_alert_log   <-- Hermez output (log only)

Invariant: Hermez reads only hr_daily_summary and fin_daily_summary. It never reads raw hr_attendance, hr_payroll, fin_pos_daily, fin_supplier_cost, fin_petty_cash, or fin_expense. Raw sheets remain the responsibility of the HR and Finance apps.

## 10.2 Output schemas — Hermez-owned log sheets

Hermez writes only to these two sheets. It never writes to any HR/Finance sheet.

### 10.2.1 hermezdailybrief

| # | Column | Type | Format | Required | Example |
| --- | --- | --- | --- | --- | --- |
| 1 | date | date | YYYY-MM-DD | Yes | 2026-06-29 |
| 2 | generated_at | datetime | YYYY-MM-DD HH:MM:SS+07:00 | Yes | 2026-06-29 22:05:00+07:00 |
| 3 | brief_text | text (multiline) | Telegram-formatted | Yes | (see Section 10.4) |
| 4 | alert_level | enum | green \¦ yellow \¦ red | Yes | yellow |
| 5 | sent_to_owner | bool | true/false | Yes | true |
| 6 | sent_at | datetime | YYYY-MM-DD HH:MM:SS+07:00 | Yes (if sent) | 2026-06-29 22:05:12+07:00 |

One row per date (owner-level, all brands/outlets combined).

alert_level = highest severity of all alerts that day. green = no alerts, yellow = warning present, red = critical present.

brief_text stores the exact text sent to Telegram (plain text, not sheet markdown).

### 10.2.2 hermezalertlog

| # | Column | Type | Format | Required | Example |
| --- | --- | --- | --- | --- | --- |
| 1 | alert_id | string | ALR-YYYYMMDD-<seq> | Yes | ALR-20260629-003 |
| 2 | date | date | YYYY-MM-DD | Yes | 2026-06-29 |
| 3 | brand | string | ref master_brand / ALL | Yes | YKP Kitchen |
| 4 | outlet | string | ref master_outlet / ALL | Yes | YKP Surabaya 01 |
| 5 | alert_type | enum | (see Section 10.3) | Yes | cash_diff |
| 6 | severity | enum | warning \¦ critical | Yes | warning |
| 7 | message | text | one sentence | Yes | Selisih kas -Rp25.000 di YKP Surabaya 01 |
| 8 | source_app | enum | hr \¦ finance | Yes | finance |
| 9 | status | enum | open \¦ ack \¦ resolved | Yes | open |
| 10 | action_taken | text | free / none | Yes | none |

status defaults to open. Changed to ack/resolved only via owner/manager manual input — Hermez never auto-resolves.

action_taken is filled by the owner after execution; Hermez never fills it.

## 10.3 Alert type enum

late_staff
cash_diff
supplier_overdue
petty_cash_anomaly
high_expense
schema_mismatch
data_missing

## 10.4 Trigger / threshold rules

All thresholds are configurable in hermez_config (key-value). The values below are conservative V1 defaults. The owner must review them before pilot.

| Alert type | Source sheet | Condition | Severity default | Message template |
| --- | --- | --- | --- | --- |
| late_staff | hrdailysummary | staff_late / total_staff >= 0.30 OR staff_late >= 3 (whichever is stricter) | warning | {n} staff telat di {outlet} ({pct}% dari {total}) |
| late_staff | hrdailysummary | staff_late / total_staff >= 0.50 | critical | Krisis absensi: {n}/{total} telat di {outlet} |
| cash_diff | findailysummary | abs(cash_difference) >= 50_000 | warning | Selisih kas {diff} di {outlet} |
| cash_diff | findailysummary | abs(cash_difference) >= 200_000 | critical | Selisih kas besar {diff} di {outlet} — audit wajib |
| supplier_overdue | findailysummary | unpaid_supplier > 0 AND invoice age >= 7 days (see note) | warning | Supplier overdue {amount} di {outlet} |
| supplier_overdue | findailysummary | unpaid_supplier > 0 AND age >= 14 days | critical | Supplier overdue kritis {amount} di {outlet} — risiko supply stop |
| petty_cash_anomaly | findailysummary | petty_cash_out >= 300_000 | warning | Petty cash keluar tinggi {amount} di {outlet} |
| petty_cash_anomaly | findailysummary | petty_cash_out >= 1_000_000 | critical | Petty cash abnormal {amount} di {outlet} — cek nota |
| high_expense | findailysummary | expense / revenue >= 0.40 (margin ratio) | warning | Expense ratio {pct}% di {outlet} (rev {rev}) |
| high_expense | findailysummary | expense > revenue (loss) | critical | Loss operasional {outlet}: expense {exp} > revenue {rev} |
| schema_mismatch | hr/fin | brand/outlet does not match master | warning | Baris {sheet} tanggal {date}: brand/outlet tidak dikenal |
| data_missing | hr/fin | summary row is null/missing for an outlet that should exist | warning | Tidak ada summary {sheet} untuk {outlet} tanggal {date} |

Note:

supplier_overdue requires invoice age. fin_daily_summary only carries unpaid_supplier (amount). Age lives in fin_supplier_cost (raw), which Hermez does not read. For V1, treat unpaid_supplier > 0 as overdue when the Finance app flags it via major_finance_issue containing "overdue" or "jatuh tempo". Alternative: add unpaid_supplier_age_days to fin_daily_summary (upgrade path; see Section 10.7).

Threshold ratios for staff late (0.30/0.50) and expense (0.40) are defaults; owner must calibrate after the 7-day pilot.

## 10.5 Brief generation logic

Pseudocode for the daily Hermez run:

def generate_daily_brief(date: str) -> dict:
    hr_rows  = read_sheet("hr_daily_summary",  filter=date)
    fin_rows = read_sheet("fin_daily_summary", filter=date)

    # 1. Validate schema + master refs
    hr_rows, hr_issues   = validate(hr_rows,  master_brand_outlet)
    fin_rows, fin_issues = validate(fin_rows, master_brand_outlet)

    # 2. Aggregate per brand/outlet + group total
    hr_agg  = aggregate_hr(hr_rows)
    fin_agg = aggregate_fin(fin_rows)

    # 3. Evaluate triggers -> alerts
    alerts = []
    alerts += check_late_staff(hr_rows)
    alerts += check_cash_diff(fin_rows)
    alerts += check_supplier_overdue(fin_rows)
    alerts += check_petty_cash(fin_rows)
    alerts += check_high_expense(fin_rows)
    alerts += hr_issues + fin_issues  # schema/data_missing

    # 4. Determine alert_level = max severity
    level = "green" if not alerts else ("red" if any(a.severity=="critical") else "yellow")

    # 5. Compose brief_text (see Section 10.6 format)
    brief_text = compose_brief(date, hr_agg, fin_agg, alerts)

    # 6. Write log ONLY (no write-back to HR/Finance)
    brief_id = write_log("hermez_daily_brief", {
        "date": date, "generated_at": now(), "brief_text": brief_text,
        "alert_level": level, "sent_to_owner": False, "sent_at": None,
    })
    for a in alerts:
        write_log("hermez_alert_log", a.as_row())

    # 7. Send Telegram if level != green OR owner opt-in green
    if level != "green" or owner_wants_green:
        send_telegram(brief_text)
        update_brief(brief_id, sent_to_owner=True, sent_at=now())

    return {"brief_id": brief_id, "level": level, "alert_count": len(alerts)}

Composition rules:

Section order: Header → Finance (revenue, expense, profit) → HR (attendance) → Alerts list → Action for tomorrow.

If no alerts → level green; brief still sent if owner opts in (default: send only yellow/red).

Rupiah numbers are formatted as Rp1.234.000 in brief_text; stored as integers.

Outlets without a summary row generate a data_missing alert and are excluded from aggregates.

## 10.6 Telegram output format

Template brief_text (plain text, newline-separated, safe for Telegram plain mode):

YKP Daily Brief - 29 Jun 2026
Level: YELLOW

[Finance]
- Total revenue: Rp12.450.000
- Total expense: Rp3.200.000
- Net profit estimate: Rp8.450.000
- Unpaid supplier: Rp2.300.000

[HR]
- Total staff: 16 | Present: 14 | Late: 3 | Absent: 2

[Alerts] (2)
- [warning] 3 staff telat di YKP Surabaya 01 (37% dari 8)
- [warning] Selisih kas -Rp25.000 di YKP Surabaya 01

[Action besok]
- Audit closing kas YKP Surabaya 01
- Briefing SPV absensi

Rules:

Header is always YKP Daily Brief - DD MMM YYYY.

Empty sections still appear with label and value none/0 (do not drop sections — owner checks completeness).

[Alerts] shows (N) = alert count. Each alert is one line prefixed with [severity].

[Action besok] is derived from combined recommended_action from HR + Finance plus critical alerts. Max 5 lines.

Max length 4096 characters (Telegram limit). If exceeded, split by brand/outlet and send sequentially.

## 10.7 No-write-back policy

Hermez does not edit data or transfer money automatically. All actions still require owner/manager approval.

Hermez only reads summaries, creates daily briefs, alerts, insights, and weekly reports.

Do not make Hermez an operational input surface.

Technical contract:

Hermez is read-only on hr_daily_summary, fin_daily_summary, master_brand, master_outlet.

Hermez is write-only on hermez_daily_brief, hermez_alert_log (its own output sheets).

Hermez never writes to hr_attendance, hr_payroll, fin_pos_daily, fin_supplier_cost, fin_petty_cash, fin_expense, or any master sheet.

No API call to the HR/Finance app mutates data.

hermez_alert_log.status changes only via owner/manager manual input — Hermez does not auto-ack or auto-resolve.

Execution of actions (audit, transfer, briefing) is done by humans, not Hermez. Hermez only recommends in brief_text.

Technical enforcement:

Hermez service account: read-only scope on HR/Finance workbooks; write scope only on Hermez output sheets (YKP_HERMEZ_OUTPUT or a tab in YKP_CENTRAL_DATABASE).

Audit log: every sheet access is logged (timestamp, sheet, read/write mode).

Kill switch: env var HERMEZ_WRITEBACK_ENABLED=false (hard default). Even if code accidentally calls write, the service account scope blocks it.

## 10.8 Scheduling

| Job | Trigger | Time (WIB) | Source | Output |
| --- | --- | --- | --- | --- |
| Daily brief generate | Daily cron | 22:00 | hr/findailysummary for day H | hermezdailybrief + hermezalertlog |
| Daily brief send Telegram | After generate | 22:00–22:05 | Brief for day H | Telegram owner |
| Retry send on failure | Cron 15 min later | 22:15 | Brief for day H not yet sent_to_owner=true | Telegram |
| Weekly insight (V1.1) | Weekly cron | Monday 08:00 | 7 days of briefs + alerts | hermezweeklyinsight (new sheet) |

Rules:

22:00 is chosen because outlet closing is typically 21:00 and app summaries are usually filled by ~21:30. Buffer 30 minutes.

If day H summary is missing at 22:00, generate brief with data_missing alert per outlet and still send (minimum level yellow).

Idempotent: re-running for day H overwrites the same hermez_daily_brief row (unique key date). Alert log duplicates are avoided by checking alert_id before insert.

Timezone: Asia/Jakarta (+07:00). All date values are local dates, not UTC.

## 10.9 Upgrade path (outside V1 scope)

Marked with ponytail: — skip in V1, add when triggered:

unpaid_supplier_age_days column in fin_daily_summary → accurate supplier_overdue without heuristic. Add when Finance app is stable and owner needs aging report.

Weekly insight sheet + Monday cron. Add when 30 days of brief data is collected.

Operational/Marketing summary sheets following the same pattern (ops_daily_summary, mkt_daily_summary). Add when those apps are running.

Auto-ack alert from Telegram button. Add when owner is comfortable with high alert volume.

Threshold auto-tuning from 30-day rolling. Add when data is sufficient and owner requests auto-calibration.

→ skipped: accurate aging, weekly insight, multi-domain summaries, auto-ack, auto-tune. add when [30-day pilot complete + owner request].

# 11. Implementation Roadmap

## 11.1 Phase 0 — Setup (Week 1)

| # | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 0.1 | Create YKP testing environment (spreadsheet IDs, service accounts, app clone) | DevOps | Test env URLs + credentials vault |
| 0.2 | Define master_brand, master_outlet initial list with Operations | Ops | Master sheet populated |
| 0.3 | Backup any existing production data before migration | DevOps | Backup stored |
| 0.4 | Set up shared secret/env management (see Appendix B) | DevOps | .env template + vault |

## 11.2 Phase 1 — HR Migration (Weeks 1–3)

| # | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 1.1 | Clone HR app to test env | Dev | Running test instance |
| 1.2 | Connect HR app to YKP_HR_DATABASE | Dev | Verified read/write |
| 1.3 | Remove dummy data | Dev + Data | Clean database |
| 1.4 | Fill master_employee roster | HR/Ops | Employee records validated |
| 1.5 | Configure hr_rules per outlet | Ops + Dev | Rules in app admin |
| 1.6 | Test attendance + payroll on samples | QA + Finance | Variance ≤ Rp 1,000 |
| 1.7 | Build hr_daily_summary generator | Dev | Summary contract satisfied |
| 1.8 | HR 7-day pilot at one outlet | Ops | Daily closure clean |

## 11.3 Phase 2 — Finance Migration (Weeks 2–5)

| # | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 2.1 | Clone Finance app to test env | Dev | Running test instance |
| 2.2 | Connect Finance app to YKP_FINANCE_DATABASE | Dev | Verified read/write |
| 2.3 | Remove dummy data | Dev + Data | Clean database |
| 2.4 | Fill finance masters (supplier, categories, payment methods, petty cash accounts) | Finance/Ops | Master sheets populated |
| 2.5 | Enter opening balances | Finance/Ops | Signed-off balances |
| 2.6 | Import Moka POS sample (3–7 days) | Data + Dev | fin_pos_daily matches Moka |
| 2.7 | Input supplier/petty cash/expense samples with evidence | Finance/Ops | All rows have attachments |
| 2.8 | Validate dashboard formulas vs manual P&L | QA + Finance | Variance ≤ 2% |
| 2.9 | Build fin_daily_summary generator | Dev | Summary contract satisfied |
| 2.10 | Finance 7-day pilot at one brand/outlet | Ops | Daily validation passes |

## 11.4 Phase 3 — Hermez (Weeks 4–6)

| # | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 3.1 | Set up Hermez service account with read-only scope on HR/Finance summaries | DevOps | IAM + sheet permissions |
| 3.2 | Implement hermez_daily_brief + hermez_alert_log writers | Dev | Output schemas working |
| 3.3 | Implement validation, aggregation, trigger evaluation, brief composition | Dev | Brief generated for sample dates |
| 3.4 | Integrate Telegram send + retry | Dev | Test channel receives messages |
| 3.5 | Wire daily cron at 22:00 WIB | DevOps | Cron scheduled + monitored |
| 3.6 | 7-day Hermez pilot alongside HR/Finance pilot | Ops + QA | Briefs match reality, alerts accurate |

## 11.5 Phase 4 — Rollout (Week 6+)

| # | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 4.1 | Promote HR app to production per outlet | Dev + Ops | Each outlet passes 1-day smoke test |
| 4.2 | Promote Finance app to production per brand/outlet | Dev + Ops | Each passes 1-day smoke + Moka reconciliation |
| 4.3 | Promote Hermez to production Telegram channel | DevOps | Owner receives live briefs |
| 4.4 | Archive test environment or freeze it as staging | DevOps | Clear env separation |

# 12. Pilot Plan

## 12.1 Pilot scope

One brand, one outlet, 7 consecutive operational days.

Run HR, Finance, and Hermez together during the pilot.

Do not expand to a second outlet until the first passes all gates.

## 12.2 Pilot checklist (daily)

| # | Check | Evidence | Tolerance |
| --- | --- | --- | --- |
| 1 | hr_attendance closes cleanly every day | No open checkouts older than 48 hours | 0 exceptions |
| 2 | hr_daily_summary produced for the outlet | Sheet row exists | 0 missing days |
| 3 | fin_pos_daily matches Moka report | Moka export vs app row | ≤ 1% or Rp 10,000 |
| 4 | Petty cash physical count matches system | Count sheet vs fin_petty_cash | ≤ Rp 5,000 or explained |
| 5 | Cash register physical count matches system | Closing count vs formula | = cash_difference within Rp 5,000 |
| 6 | Supplier invoices match fin_supplier_cost | Invoice photo + number match | 100% of sample rows |
| 7 | fin_daily_summary produced for the outlet | Sheet row exists | 0 missing days |
| 8 | Hermez brief generated at 22:00 and sent | Telegram log + hermez_daily_brief row | Sent within 22:05 WIB |
| 9 | Hermez alerts match real conditions | Manager sign-off | No false positives/negatives |
| 10 | All variances logged and explained | Issue log | All critical items resolved |

## 12.3 Pilot exit criteria

All of the following must be true for 7 consecutive days before rollout:

HR attendance closes with 0 unexplained open checkouts.

Finance dashboard variance vs Moka/manual ≤ tolerance every day.

Cash difference is either zero or explained and signed off.

Hermez briefs are generated and sent on time with accurate alert levels.

No unresolved critical alerts older than 24 hours.

Backup of pre-pilot state exists.

# 13. Definition of Done

## 13.1 HR App

[ ] HR app cloned and running in YKP testing environment.

[ ] App connected to YKP_HR_DATABASE with verified read/write.

[ ] Dummy/demo data removed.

[ ] master_brand, master_outlet, master_employee populated with no orphan records.

[ ] hr_rules configured for every active outlet.

[ ] Attendance check-in/out, late, izin, missing checkout tested and correct.

[ ] Payroll gross matches manual calculation for 3–5 sample employees within Rp 1,000.

[ ] hr_daily_summary generated daily and satisfies the contract in Section 9.1.

[ ] 7-day pilot at one outlet completed successfully.

[ ] Backup of YKP_HR_DATABASE taken before rollout.

## 13.2 Finance App

[ ] Finance app cloned and running in YKP testing environment.

[ ] App connected to YKP_FINANCE_DATABASE with verified read/write.

[ ] Dummy/demo data removed.

[ ] Finance masters (supplier, categories, payment methods, petty cash accounts) populated.

[ ] Opening balances entered and signed off per outlet.

[ ] fin_pos_daily matches Moka for 3–7 sample days within tolerance.

[ ] Supplier, petty cash, and expense rows have evidence attachments.

[ ] Dashboard formulas reconcile to manual P&L within 2%.

[ ] fin_daily_summary generated daily and satisfies the contract in Section 9.2.

[ ] 7-day pilot at one brand/outlet completed with no unresolved cash or supplier mismatches.

[ ] Backup of YKP_FINANCE_DATABASE taken before rollout.

## 13.3 Hermez AI Layer

[ ] Hermez reads hr_daily_summary + fin_daily_summary without schema errors.

[ ] Daily brief generated at 22:00 WIB and sent to Telegram.

[ ] hermez_daily_brief + hermez_alert_log written according to the contracts in Section 10.2.

[ ] 5 business triggers active (late_staff, cash_diff, supplier_overdue, petty_cash_anomaly, high_expense) + 2 system triggers (schema_mismatch, data_missing).

[ ] No writes detected to HR/Finance sheets (audit log clean).

[ ] Owner/manager can manually change hermez_alert_log.status without Hermez overwriting it.

[ ] 7-day pilot: briefs sent on time, alerts match reality, numbers match Moka/manual.

## 13.4 Verification (smoke-test each layer)

### 13.4.1 Master DB smoke test

Open YKP_MASTER_DATABASE.

Confirm master_brand has ≥1 active brand with brand_id in format BR-NNN.

Confirm every master_outlet row has a valid brand_id referencing master_brand.

Confirm every master_employee row has a valid outlet_id and brand_id.

Confirm master_supplier rows are active/inactive, not dummy.

### 13.4.2 HR app smoke test

Log in to the HR test app.

Create one attendance record: check-in, check-out, late, izin, absent.

Verify hr_attendance stores dates in YYYY-MM-DD and times in HH:mm:ss WIB.

Run payroll for one sample employee and compare gross to manual calc.

Confirm hr_daily_summary is produced for the sample date with correct total_staff, staff_present, staff_late, staff_absent.

### 13.4.3 Finance app smoke test

Log in to the Finance test app.

Import or manually enter one fin_pos_daily row matching a Moka daily report.

Enter one supplier invoice, one petty cash out, one expense with attachment URL.

Verify dashboard revenue, expense, supplier cost, petty cash out, unpaid supplier, net profit estimate.

Compare net profit estimate to a manually reconstructed P&L; variance must be ≤ 2%.

Confirm fin_daily_summary is produced for the sample date with all required columns.

### 13.4.4 Hermez smoke test

Ensure hr_daily_summary and fin_daily_summary each have at least one row for the same date.

Trigger the Hermez daily job manually or wait for 22:00 cron.

Open hermez_daily_brief and confirm a row exists for the date with alert_level, brief_text, generated_at.

Confirm Telegram test channel received the brief (or sent_to_owner is false if intentionally suppressed).

Open hermez_alert_log and confirm any expected alerts were written with alert_id, severity, status = open.

Attempt to write to hr_daily_summary or fin_daily_summary with the Hermez service account and confirm it is denied by sheet permissions.

### 13.4.5 Integration smoke test

Change one attendance status in the HR app.

Re-run hr_daily_summary.

Re-run Hermez for the same date.

Confirm the brief reflects the updated staff counts.

Change one fin_pos_daily net_sales value.

Re-run fin_daily_summary and Hermez.

Confirm revenue and net profit estimate update in the brief.

### 13.4.6 Rollout smoke test

Promote to one additional outlet.

Run one full operational day.

At closing, confirm HR attendance closes, Finance summary matches Moka, and Hermez brief is generated.

If any step fails, rollback to the pre-rollout backup and fix in test env.

# 14. Risks & Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Dummy data leaks into production | Medium | High | DoD gate: zero dummy rows allowed; nightly reconciliation; explicit quarantine process |
| Moka numbers do not match fin_pos_daily | High | High | Daily Moka reconciliation with ≤1% / Rp 10,000 tolerance; block rollout on failure |
| Cash difference unexplained every day | Medium | High | Physical cash count at closing; variance ≤ Rp 5,000 or explained; unresolved diff blocks rollout |
| HR app timezone stores UTC | Low | High | Force Asia/Jakarta in app and DB; validation smoke test checks date alignment |
| Supplier invoices missing evidence | Medium | Medium | 100% attachment requirement for sample rows; Finance app rejects rows without source/recorded_by |
| Hermez reads raw sheets by mistake | Low | High | Service-account permissions deny raw sheets; audit log; kill switch HERMEZ_WRITEBACK_ENABLED=false |
| Hermez false alerts overwhelm owner | Medium | Medium | Conservative default thresholds; owner calibration after 7-day pilot; opt-in green briefs |
| Spreadsheet ID swapped without schema audit | Medium | High | Never swap ID without checking tab names, columns, formulas, permissions; use env-specific IDs |
| Master data duplicated between HR and Finance DBs | Medium | High | YKP_MASTER_DATABASE is single source of truth; FK checks in domain apps |
| Pilot expanded too early | Medium | High | Hard gate: 7 consecutive days within tolerance; manager sign-off; backup before each rollout |
| Service account credentials exposed | Low | Critical | Store in vault only; never commit secrets; rotate if leaked; separate test/prod credentials |

# 15. Short Developer Message / Next Actions

What to do next (in order):

Set up the testing environment. Create/clone the HR and Finance apps, create the three spreadsheet databases, and configure service accounts. Do not touch production.

Populate masters. Fill master_brand, master_outlet, master_employee, and master_supplier with real YKP data. No placeholders.

Migrate HR first. It is the greenest path. Get attendance and payroll working, then produce hr_daily_summary.

Migrate Finance second. Validate every number against Moka and physical counts before building fin_daily_summary.

Wire Hermez last. Only after both summary sheets are live and validated. Start with the test Telegram channel.

Run the 7-day pilot. One brand, one outlet. Do not expand until all gates pass.

Golden rule for this project: Reuse the apps, replace the data, validate the numbers, then let Hermez read summaries. If a task does not serve one of those four things, question whether it belongs in V1.

# Appendix A: Google Sheets Formula Examples

## A.1 Master lookup helpers

=IFERROR(VLOOKUP(A2, master_brand!A:B, 2, FALSE), "UNKNOWN")

Looks up brand_name from brand_id. Use IFERROR so invalid refs surface as UNKNOWN, not silently blank.

## A.2 HR attendance count

=COUNTIFS(hr_attendance!B:B, DATE(2026,6,29),
          hr_attendance!E:E, "present",
          hr_attendance!D:D, A2)

Counts present employees for outlet A2 on a given date. Adjust ranges to match actual columns.

## A.3 Late staff count

=COUNTIFS(hr_attendance!B:B, DATE(2026,6,29),
          hr_attendance!D:D, A2,
          hr_attendance!J:J, TRUE)

Counts rows where is_late is TRUE.

## A.4 Daily revenue

=SUMIFS(fin_pos_daily!E:E,
        fin_pos_daily!B:B, DATE(2026,6,29),
        fin_pos_daily!D:D, A2)

Sums net_sales for outlet A2 on the given date.

## A.5 Expense total

=SUMIFS(fin_expense!F:F,
        fin_expense!B:B, DATE(2026,6,29),
        fin_expense!D:D, A2)

Sums amount for outlet A2 on the given date.

## A.6 Petty cash out

=SUMIFS(fin_petty_cash!F:F,
        fin_petty_cash!B:B, DATE(2026,6,29),
        fin_petty_cash!D:D, A2,
        fin_petty_cash!G:G, "out")

Sums petty cash outflows.

## A.7 Unpaid supplier

=SUMIFS(fin_supplier_cost!H:H,
        fin_supplier_cost!D:D, A2,
        fin_supplier_cost!J:J, "<>paid")

Sums unpaid_amount where status is not paid.

## A.8 Net profit estimate

=B2 - C2 - D2 - E2

Where B2 = revenue, C2 = expense, D2 = supplier_cost, E2 = petty_cash_out.

## A.9 Cash difference

=(opening_cash + cash_revenue_in - cash_expense_out - petty_cash_out) - physical_cash_count

This formula depends on opening balance and physical closing count. Store opening balance in fin_opening_balance.cash_balance and physical count in a closing-cash input sheet or column.

## A.10 Hermez alert level

=IF(COUNTIF(hermez_alert_log!D:D, "critical") > 0, "red",
    IF(COUNTIF(hermez_alert_log!D:D, "warning") > 0, "yellow", "green"))

Returns the highest severity for a given date.

# Appendix B: Environment Variables & Secrets

## B.1 Required environment variables

| Variable | Purpose | Example | Notes |
| --- | --- | --- | --- |
| YKP_MASTER_DATABASE_ID | Spreadsheet ID for master data | 1xYz... | Shared read |
| YKP_HR_DATABASE_ID | Spreadsheet ID for HR domain | 1aBc... | HR app write, Hermez summary read |
| YKP_FINANCE_DATABASE_ID | Spreadsheet ID for Finance domain | 1dEf... | Finance app write, Hermez summary read |
| YKP_HERMEZ_OUTPUT_ID | Spreadsheet ID for Hermez logs | 1gHi... | Hermez write |
| HERMEZ_TELEGRAM_BOT_TOKEN | Telegram bot token | 123456:ABC... | Secret |
| HERMEZ_TELEGRAM_OWNER_CHAT_ID | Owner/manager chat ID | -1001234567890 | Secret |
| HERMEZ_TELEGRAM_TEST_CHAT_ID | Test channel chat ID | -1009876543210 | Secret |
| HERMEZ_TIMEZONE | All date math | Asia/Jakarta | Hard default |
| HERMEZ_WRITEBACK_ENABLED | Kill switch | false | Must stay false in V1 |
| HERMEZ_RUN_HOUR_UTC | Cron hour in UTC | 15 | 15:00 UTC = 22:00 WIB |
| GOOGLE_SERVICE_ACCOUNT_HR | Path/JSON for HR app credentials | /secrets/hr-sa.json | HR app only |
| GOOGLE_SERVICE_ACCOUNT_FINANCE | Path/JSON for Finance app credentials | /secrets/finance-sa.json | Finance app only |
| GOOGLE_SERVICE_ACCOUNT_HERMEZ | Path/JSON for Hermez credentials | /secrets/hermez-sa.json | Hermez only; read-only on HR/Finance |

## B.2 Secret handling rules

Never commit secrets to the repository.

Use a vault (e.g., Google Secret Manager, AWS Secrets Manager, or 1Password) in production.

For local/testing, use .env files that are ignored by git.

Separate service accounts for test and production environments.

Rotate credentials if any file is accidentally exposed.

## B.3 Sample .env template (for local dev only)

# DANGER: do not commit this file
YKP_MASTER_DATABASE_ID=1xYz...
YKP_HR_DATABASE_ID=1aBc...
YKP_FINANCE_DATABASE_ID=1dEf...
YKP_HERMEZ_OUTPUT_ID=1gHi...
HERMEZ_TELEGRAM_BOT_TOKEN=123456:ABC...
HERMEZ_TELEGRAM_OWNER_CHAT_ID=-1001234567890
HERMEZ_TELEGRAM_TEST_CHAT_ID=-1009876543210
HERMEZ_TIMEZONE=Asia/Jakarta
HERMEZ_WRITEBACK_ENABLED=false
HERMEZ_RUN_HOUR_UTC=15
GOOGLE_SERVICE_ACCOUNT_HR=/secrets/hr-sa.json
GOOGLE_SERVICE_ACCOUNT_FINANCE=/secrets/finance-sa.json
GOOGLE_SERVICE_ACCOUNT_HERMEZ=/secrets/hermez-sa.json

End of blueprint.